## Sheet1
Milestone | ETA | Task | Sub-Task | Priority | Difficulty
Draft 1 (rough cut) | 20101203 | Overview 'neural algorithms' |  | Medium | High
|  | Overview 'probabilistic algorithms' |  | Medium | High
|  | Overview 'physical algorithms' |  | Medium | High
|  | Collate book (all algorithms into book structure) |  | High | Low
|  | Algorithm implementation 'once over' |  | Low | Medium
|  | Send out manuscripts for tech editing |  | High | Low
Draft 2 (all content) | 20101231 | Final 5 Algorithms | Algorithm 1 | Medium | High
|  | " " | Algorithm 2 | Medium | High
|  | " " | Algorithm 3 | Medium | High
|  | " " | Algorithm 4 | Medium | High
|  | " " | Algorithm 5 | Medium | High
|  | Fix known algorithm bugs |  | High | High
|  | Introduction amendment 'when to use' |  | Medium | Medium
|  | Appendix: Ruby Crash Course |  | Low | Medium
|  | Advanced Chapters | Programming Paradigms | Medium | Medium
|  | " " | Devising New Algorithms | High | Medium
|  | " " | Unit Testing Algorithms | Medium | Medium
|  | " " | Visualizing Algorithms | High | Medium
|  | " " | Problem Solving Method | High | Medium
|  | " " | Racing Algorithms | High | Medium
|  | Send out manuscripts for 'deep' copy editing |  | High | Low
Draft 3 (finalized) | 20110120 | Tender cover on 99designs |  | Medium | Medium
|  | Complete unit tests for all algorithms |  | Medium | Medium
|  | Create lulu account for book |  | High | Low
|  | Update book structure for Lulu format |  | Medium | Low
|  | Consolidate technical/other edits |  | High | Medium
Version 1.0 | 20110126 | Final cover design |  | High | Low
|  | Book on Lulu |  | High | Low
|  | Website with all content |  | Low | High